## BIMcollab Report
|  |  |  | Project name |  | BIMcollab Example project
|  |  |  | Creator |  | Fred Leopard
|  |  |  | Organization |  | Example BIM coordination inc.
|  |  |  | Date |  | 29-12-2017 11:01
|  |  |  | Filter settings |  | All 22 issues in this project
Snapshot | Nr | Title | Status | Created | Created by | Assigned to | Type | Priority | Area | Milestone | Deadline | Labels | Approval
| 1 | Intersections check: beam inside wall | Resolved | 16-10-2014 10:00 | Fred Leopard | Fred Leopard | Issue | Normal | BIM Model protocol | 01. Design phase | 31-12-2017 | Architecture
| 2 | Intersections check: column inside slab | Active | 16-10-2014 10:01 | Fred Leopard | Fred Leopard | Issue | Normal | BIM Model protocol | 01. Design phase | 31-12-2017 | Architecture
| 3 | Intersections check: wall inside wall | Resolved | 16-10-2014 09:57 | Fred Leopard | Fred Leopard | Issue | Normal | BIM Model protocol | 01. Design phase | 31-12-2017 | Architecture | Betty Gizzy, Blake Green
| 4 | Intersections check: ceiling inside wall | Closed | 16-10-2014 10:02 | Fred Leopard | Fred Leopard | Issue | Normal | BIM Model protocol | 01. Design phase | 31-12-2017 | Architecture
| 5 | Duplicate components check sanitary terminal | Active | 16-10-2014 09:54 | Fred Leopard | Blake Green | Issue | Normal | BIM Model protocol | 01. Design phase | 31-12-2017 | Architecture
| 6 | Duplicate components check sanitary terminal | Active | 16-10-2014 09:55 | Fred Leopard | Blake Green | Issue | Normal | BIM Model protocol | 01. Design phase | 31-12-2017 | Architecture
| 7 | Ducts are designed in elevator shaft. | Active | 16-10-2014 13:11 | Betty Gizzy | Dwayne Parsons | Clash | Normal | Main Building | 01. Design phase | 31-12-2017 | Structure, Mechanical
| 8 | Hollow core slab and sewer are clashing. | Active | 16-10-2014 14:12 | Fred Leopard | Dwayne Parsons | Issue | Normal | Main Building | 01. Design phase | 31-12-2017 | Mechanical, Structure | Betty Gizzy
| 9 | Intersections of slab | Active | 16-10-2014 14:08 | Fred Leopard | Irwin Renfroe | Issue | Normal | Main Building | 01. Design phase | 31-12-2017 | Architecture, Structure, Mechanical
| 10 | Intersections of column | Active | 16-10-2014 14:07 | Fred Leopard | Betty Gizzy | Clash | Normal | Main Building | 01. Design phase | 31-12-2017 | Architecture, Structure, Mechanical
| 11 | Intersection ventilation and wall | Active | 16-10-2014 14:10 | Fred Leopard | Irwin Renfroe | Clash | Normal | Main Building | 01. Design phase | 31-12-2017 | Architecture, Structure, Mechanical
| 12 | Pipe too close to window component | Active | 16-10-2014 14:13 | Fred Leopard | Dwayne Parsons | Issue | Normal | Main Building | 01. Design phase | 31-12-2017 | Architecture, Mechanical
| 16 | Atrium is interrupted by ventilation duct | Active | 16-10-2014 15:24 | Blake Green | Blake Green | Issue | Normal | Interior general | 01. Design phase | 31-12-2017 | Architecture, Mechanical
| 17 | Layout of main entrance | Active | 16-10-2014 15:21 | Blake Green | Blake Green | Issue | Normal | Interior general | 01. Design phase | 31-12-2017 | Architecture
| 13 | Ventilation duct too close to wall | Active | 16-10-2014 14:45 | Fred Leopard | Jane Holloway | Issue | Normal | Main Building | 02. Engineering Phase | 31-10-2018 | Architecture, Structure, Mechanical
| 14 | Sewer and hollowcore slab intersections | Active | 16-10-2014 14:36 | Fred Leopard | Stewart Mendoza | Issue | Normal | Main Building | 02. Engineering Phase | 31-10-2018 | Structure, Mechanical
| 15 | Ventilation and prefab concrete | Active | 16-10-2014 14:42 | Fred Leopard | Stewart Mendoza | Clash | Normal | Main Building | 02. Engineering Phase | 31-10-2018 | Structure
| 18 | Shapes on outside of building | Active | 16-10-2014 15:19 | Blake Green | Blake Green | Issue | Normal | Main Building | 01. Design phase | 31-12-2017 | Architecture
| 19 | Ventilation in auditorium | Active | 16-10-2014 15:28 | Blake Green | Blake Green | Issue | Normal | Interior general | 01. Design phase | 31-12-2017 | Architecture, Mechanical
| 20 | Balcony | Active | 16-10-2014 15:26 | Blake Green | Blake Green | Request | Normal | Main Building | 01. Design phase | 31-12-2017 | Architecture
| 21 | Ceiling above reception | Active | 16-10-2014 15:35 | Blake Green | Irwin Renfroe | Inquiry | Normal | Interior general | 01. Design phase | 10-10-2017 | Architecture
| 22 | Sitework progress is slow | Active | 16-10-2014 15:38 | Fred Leopard | Fred Leopard | Issue | Normal | Terrain | 03. Construction phase | 31-12-2019